## Sheet1
File/PO | Item | FIRM Name | PO Value | Vr. no | Vr. Date | VrAmt | PO/Rel Dt | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 91 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 680 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 603 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 774 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 | 6824 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 506 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6825 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 841 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6829 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 240 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6829 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 612 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6835 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 288 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 342 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 276 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 605 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 484 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 404 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 | 6878 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 100 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6882 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 638 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6882 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 478 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 43 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 185 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 775 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 492 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 | 6912 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 481 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6913 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 603 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 | 6926 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 482 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 | 6942 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 319 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 640 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 341 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 784 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6994 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 514 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6994 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 790 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 | 7022 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 745 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1

## FORMATS
File/PO | Item | FIRM Name | PO-val[L] | Vr. no | Vr. Date | VrAmt | PO-Rel-dt. | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO/ CODE | CODE | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
A | CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE | B | 500 | 91 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION | B | 600 | 680 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM | B | 700 | 603 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM | B | 800 | 774 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 | 6824 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
A | Providing Standby AC system for server room of MPS at FRFCF | B | 900 | 506 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6825 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5