## Sheet1
File/PO | Item | FIRM Name | PO Value | Vr. no | Vr. Date | VrAmt | PO/Rel Dt | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 91 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 680 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 603 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 774 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 | 6824 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 506 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6825 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 841 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6829 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 240 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6829 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 612 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6835 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 288 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 342 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 276 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 605 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 484 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 404 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 | 6878 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 100 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6882 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 638 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6882 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 478 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 43 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 185 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 775 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 492 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 | 6912 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 481 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6913 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 603 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 | 6926 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 482 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 | 6942 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 319 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 640 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 341 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 784 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6994 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 514 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6994 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 790 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 | 7022 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 745 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 745 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1

## FORMATS
File/PO | Item | FIRM Name | PO-val[L] | Vr. no | Vr. Date | VrAmt | PO-Rel-dt. | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO/ CODE | CODE | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
A | CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE | B | 500 | 91 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION | B | 600 | 680 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM | B | 700 | 603 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM | B | 800 | 774 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 | 6824 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
A | Providing Standby AC system for server room of MPS at FRFCF | B | 900 | 506 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6825 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5

## test
File/PO | Item | FIRM Name | PO Value | Vr. no | Vr. Date | VrAmt | PO/Rel Dt | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2001 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2002 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2003 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2004 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2005 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2006 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2007 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2008 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2009 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2010 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2011 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2012 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2013 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2014 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2015 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2016 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2017 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2018 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2019 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2020 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2021 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2022 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2023 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2024 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2025 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2026 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2027 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2028 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2029 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2030 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2031 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2032 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2033 | 04/12/20134 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2034 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2035 | 2014-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2036 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2037 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2038 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2039 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2040 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2041 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2042 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2043 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2044 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2045 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2046 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2047 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2048 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2049 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2050 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2051 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2052 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2053 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2054 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2055 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2056 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2057 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2058 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2059 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2060 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2061 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2062 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2063 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2064 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2065 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2066 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2067 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2068 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2069 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2070 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2071 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2072 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2073 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2074 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2075 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2076 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2077 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2078 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2079 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2080 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2081 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2082 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2083 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2084 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2085 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2086 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2087 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2088 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2089 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2090 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2091 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2092 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2093 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2094 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2095 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2096 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2097 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2098 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2099 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2100 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2101 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2102 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2103 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2104 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2105 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2106 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2107 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2108 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2109 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2110 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2111 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2112 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2113 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2114 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2115 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2116 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2117 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2118 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2119 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2120 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2121 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2122 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2123 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2124 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2125 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2126 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2127 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2128 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2129 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2130 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2131 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2132 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2133 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2134 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2135 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2136 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2137 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2138 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2139 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2140 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2141 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2142 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2143 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2144 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2145 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2146 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2147 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2148 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2149 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2150 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2151 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2152 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2153 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2154 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2155 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2156 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2157 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2158 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2159 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2160 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2161 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2162 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2163 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2164 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2165 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2166 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2167 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2168 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2169 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2170 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2171 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2172 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2173 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2174 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2175 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2176 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2177 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2178 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2179 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2180 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2181 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2182 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2183 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2184 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2185 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2186 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2187 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2188 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2189 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2190 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2191 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2192 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 2193 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 2194 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 2195 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 2196 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 2197 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 2198 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 2199 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 2200 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 2201 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 2202 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 2203 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 2204 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 2205 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 2206 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 2207 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 2208 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 2209 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 2210 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 2211 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 2212 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 2213 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 2214 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 2215 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 2216 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 2217 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 2218 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 2219 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 2220 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 2221 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 2222 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2223 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 2224 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1