## Sheet1
File/PO | Item | FIRM Name | PO Value | Vr. no | Vr. Date | VrAmt | PO/Rel Dt | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 91 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 680 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 603 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 774 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 | 6824 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 506 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6825 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 841 | 2013-10-31 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6829 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 240 | 2014-02-07 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6829 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 612 | 2014-02-26 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6835 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 288 | 2014-01-10 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 342 | 2014-03-12 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 276 | 2013-10-09 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 605 | 2013-12-27 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 484 | 2014-02-20 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 404 | 2014-03-14 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 | 6878 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 100 | 2014-02-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6882 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 638 | 2014-03-21 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6882 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 478 | 2014-02-20 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 43 | 2013-11-01 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 185 | 2013-12-06 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 775 | 2014-01-31 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 492 | 2014-01-22 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 | 6912 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 481 | 2014-02-20 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6913 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 603 | 2014-02-26 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 | 6926 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 482 | 2014-02-20 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 | 6942 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 319 | 2014-03-12 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 640 | 2014-03-21 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 341 | 2014-03-12 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 784 | 2014-01-31 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6994 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 514 | 2014-03-18 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6994 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 790 | 2014-03-27 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 | 7022 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 745 | 2014-03-26 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 745 | 2014-03-26 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1

## FORMATS
File/PO | Item | FIRM Name | PO-val[L] | Vr. no | Vr. Date | VrAmt | PO-Rel-dt. | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO/ CODE | CODE | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
A | CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE | B | 500 | 91 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION | B | 600 | 680 | 2014-03-24 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM | B | 700 | 603 | 2013-12-27 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
A | eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM | B | 800 | 774 | 2014-01-31 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 | 6824 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
A | Providing Standby AC system for server room of MPS at FRFCF | B | 900 | 506 | 2014-03-18 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 | 6825 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5

## test
File/PO | Item | FIRM Name | PO Value | Vr. no | Vr. Date | VrAmt | PO/Rel Dt | PO/WO Completion Date | Final Payment completed Date | Status of completion (ON GOING/ COMPLETED) | O PIN | N PIN | CC NO | Paid[L] | Head of Account | New HoA | Indentor | GrpDivSec | Plant/Service | Sanction OM activity Sl.No | Sanction OM MW/ME Sl.No
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3001 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3002 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3003 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3004 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3005 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3006 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3007 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3008 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3009 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3010 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3011 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3012 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3013 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3014 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3015 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3016 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3017 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3018 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3019 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3020 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3021 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3022 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3023 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3024 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3025 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3026 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3027 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3028 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3029 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3030 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3031 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3032 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3033 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3034 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3035 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3036 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3037 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3038 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3039 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3040 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3041 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3042 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3043 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3044 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3045 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3046 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3047 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3048 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3049 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3050 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3051 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3052 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3053 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3054 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3055 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3056 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3057 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3058 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3059 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3060 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3061 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3062 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3063 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3064 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3065 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3066 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3067 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3068 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3069 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3070 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3071 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3072 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3073 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3074 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3075 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3076 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3077 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3078 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3079 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3080 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3081 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3082 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3083 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3084 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3085 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3086 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3087 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3088 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3089 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3090 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3091 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3092 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3093 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3094 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3095 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3096 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3097 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3098 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3099 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3100 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3101 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3102 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3103 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3104 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3105 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3106 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3107 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3108 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3109 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3110 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3111 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3112 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3113 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3114 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3115 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3116 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3117 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3118 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3119 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3120 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3121 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3122 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3123 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3124 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3125 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3126 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3127 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3128 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3129 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3130 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3131 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3132 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3133 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3134 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3135 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3136 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3137 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3138 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3139 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3140 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3141 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3142 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3143 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3144 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3145 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3146 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3147 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3148 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3149 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3150 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3151 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3152 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3153 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3154 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3155 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3156 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3157 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3158 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3159 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3160 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3161 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3162 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3163 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3164 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3165 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3166 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3167 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3168 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3169 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3170 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3171 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3172 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3173 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3174 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3175 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3176 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3177 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3178 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3179 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3180 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3181 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3182 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3183 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3184 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3185 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3186 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3187 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3188 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3189 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3190 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3191 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3192 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF ROAD STORM WATER DRAINAGE AND OTHER MISCELLANEOUS WORKS ON WESTERN SIDE OF DAE PLANT SITE |  | 91 | 3193 | 2013-12-04 | 23911419 | 2013-12-04 | 2015-03-01 | 2015-07-01 | COMPLETED |  | 712 | 6008 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| DEVELOPMENT AND MAINTENANCE OF LAWN AND HORTICULTURE WORK AT DIVERSION OF ROAD JUNCTION |  | 680 | 3194 | 2013-12-04 | 443118 | 2014-03-24 | 2014-10-01 | 2014-11-01 | COMPLETED |  | 712 | 6796 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING AND FIXING REPLECTIVE STUD AND PLASTIC SPEED BREAKER ON ROAD SURFACE AT DIVERSION OF ROAD KALPAKKAM |  | 603 | 3195 | 2013-12-04 | 475217 | 2013-12-27 | 2013-11-01 | 2013-12-01 | COMPLETED |  | 712 | 6798 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| eSTABLISHING DATA NETWORK IN CUBICAL SEALING ARRANGMENT AT FRFCF SITE, IGCAR KALPAKKAM |  | 774 | 3196 | 2013-12-04 | 278544 | 2014-01-31 | 2013-12-01 | 2014-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| Providing Standby AC system for server room of MPS at FRFCF |  | 506 | 3197 | 2013-12-04 | 323533 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ACV | Service | 5
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 841 | 3198 | 2013-12-04 | 256095 | 2013-10-31 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| MODIFICATION OF INTERNAL ELECTRIFICATION FOR CUBICAL SEATING ARRANGEMENT IN STORES WORKSHOP AT FRFCF |  | 240 | 3199 | 2013-12-04 | 145692 | 2014-02-07 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| LIGHTNING PROTECTION FOR INFRASTRUCTURE BUILDINGS AND ASSOCIATED ELECTRICAL WORKS AT FRFCF |  | 612 | 3200 | 2013-12-04 | 2133000 | 2014-02-26 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 288 | 3201 | 2013-12-04 | 5100172 | 2014-01-10 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF TWO NUMBERS OF SUBSTATION BUILDING FOR FRCF AT KALPAKKAM |  | 342 | 3202 | 2013-12-04 | 3291310 | 2014-03-12 | 2014-09-01 | 2014-09-01 | COMPLETED |  | 712 | 6844 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 276 | 3203 | 2013-12-04 | 1260000 | 2013-10-09 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 605 | 3204 | 2013-12-04 | 1075496 | 2013-12-27 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING HDPE PIPES CROSSING TO INSTALL HV AND CONTROL CABLES FROM IGCAR TO FRFCF KALPAKKAM |  | 484 | 3205 | 2013-12-04 | 1787402 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 | 6846 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTION FIRE HYDRANT SYSTEM FOR WASTE MANAGEMENT PLANT OF FRFCF |  | 404 | 3206 | 2013-12-04 | 4072295 | 2014-03-14 | 2014-08-01 | 2014-08-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 100 | 3207 | 2013-12-04 | 4181424 | 2014-02-04 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CONSTRUCTION OF PARKING SHED FORMATION OF ROAD AND OTHER MISCE |  | 638 | 3208 | 2013-12-04 | 2913736 | 2014-03-21 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| SUPPLY INSTALLATION TESTING AND COMMISSIONING OF ACCESS CONTROL SYSTEM |  | 478 | 3209 | 2013-12-04 | 476273 | 2014-02-20 | 2014-10-01 | 2014-10-01 | COMPLETED |  | 712 | 6892 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 43 | 3210 | 2013-12-04 | 163621 | 2013-11-01 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 185 | 3211 | 2013-12-04 | 274644 | 2013-12-06 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| CLEARENCE OF JUNGLES ALONG THE FENCING AT FRFCF SITE KALPAKKAM |  | 775 | 3212 | 2013-12-04 | 55690 | 2014-01-31 | 2014-01-01 | 2014-01-01 | COMPLETED |  | 712 | 6909 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| LAYING OF POWER AND CONTROL CABLES FROM NCSS TO FRFCF AT IGCAR KALPAKKAM |  | 492 | 3213 | 2013-12-04 | 3528410 | 2014-01-22 | 2015-01-01 | 2015-01-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| SUPPLY FABRICATION AND INSTALLATION OF WATCH TOWER |  | 481 | 3214 | 2013-12-04 | 241594 | 2014-02-20 | 2014-02-01 | 2014-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| ERRECTION AND TESTING OF DISTRIBUTION TRANSFORMER AT MAIN POWER STATION |  | 603 | 3215 | 2013-12-04 | 943760 | 2014-02-26 | 2015-02-01 | 2015-02-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| CONSTRUCTIONS OF WEIGHBRIDGE AT FRFCF |  | 482 | 3216 | 2013-12-04 | 412367 | 2014-02-20 | 2014-05-01 | 2014-05-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | MECH | Service | 7
| Providing Securigyt equipments for construction site gate of FRFCF |  | 319 | 3217 | 2013-12-04 | 3366396 | 2014-03-12 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 6943 |  | 4861 60 203 44 00 52 | 4861 03 212 06 00 53 |  | I&C | Service | 17
| PROVIDING ACCESS ROAD GATES AND OTHER MISC. WORKS FOR FRFCF |  | 640 | 3218 | 2013-12-04 | 1425180 | 2014-03-21 | 2014-11-01 | 2014-11-01 | COMPLETED |  | 712 | 6948 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 17
| WATERING THE ASSORTED TREES IN BETWEEN WATER BODY AREA TO PLANTATION AREA IN EDAIYUR BRIDGE NORTH SIDE IN KKM GATE |  | 341 | 3219 | 2013-12-04 | 28800 | 2014-03-12 | 2014-12-01 | 2014-12-01 | COMPLETED |  | 712 | 6969 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 784 | 3220 | 2013-12-04 | 312644 | 2014-01-31 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| ESTABLISHING RING FEEDER SYSTEM FOR CONSTRUCTION POWER SUPPLY AT FRFCF SITE, IGCAR, |  | 514 | 3221 | 2013-12-04 | 160346 | 2014-03-18 | 2014-03-01 | 2014-03-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | ELECT | Service | 6
| PROVIDING CHAIN LINK FINCE ON NORTHERN SIDE OF FRFCF SITE AT KALPAKKAM |  | 790 | 3222 | 2013-12-04 | 1262072 | 2014-03-27 | 2015-06-01 | 2015-06-01 | COMPLETED |  | 712 |  |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3223 | 2013-12-04 | 306880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 60 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1
| PROVIDING PVC FLOORING AND EPOXY PAINTING OVER CNC FLOOR AREA OF CENTRAL WORKSHOP BUILDING AT FRFCF SITE KALPAKKAM |  | 745 | 3224 | 2013-12-04 | 3,06,880 | 2014-03-26 | 2014-06-01 | 2014-06-01 | COMPLETED |  | 712 | 7056 |  | 4861 60 203 44 00 53 | 4861 03 212 06 00 53 |  | CIVIL | Service | 1