## Gen 1000
Name of Work | Construction of various buildings of Waste Management Plant and allied structures including Civil, Electrical and Mechanical works for FRFCF at Kalpakkam
TS No | C-0225/CV-1 (E)/FRFCF/IGCAR/2015 dt 12.01.2015
Contractor | M/s. Larsen & Toubro Limited, Chennai - 600 089
W.O NO | IGCAR/FRFCF/CV-1(E)/ETR-025/WO/2016/213 dt. 24.02.2016
Agt No. | IGCAR/FRFCF/CIVIL/A.41/2016 dt. 29.02.2016
RA-Bill No | RA BILL No. 03 (Zone-II) CC No.7732 | 1
Date of Measurement | Item No | Description of Work | Measurement Up todate |  |  |  |  | Remarks
|  |  | No | L | B | D | Content Area

## Gen 1001
Name of Work | Construction of various buildings of Waste Management Plant and allied structures including Civil, Electrical and Mechanical works for FRFCF at Kalpakkam
TS No | C-0225/CV-1 (E)/FRFCF/IGCAR/2015 dt 12.01.2015
Contractor | M/s. Larsen & Toubro Limited, Chennai - 600 089
W.O NO | IGCAR/FRFCF/CV-1(E)/ETR-025/WO/2016/213 dt. 24.02.2016
Agt No. | IGCAR/FRFCF/CIVIL/A.41/2016 dt. 29.02.2016
RA-Bill No | RA BILL No. 03 (SWB) CC No.7732 | 1
Date of Measurement | Item No | Description of Work | No. | L | B | D | Content Area | Remarks
01.06.2016 | 5.7.1 | F - 2 (Grid Aa & 4) AFL -25.151 to TOC -24.75 | 1 | 2.2 | 2.2 | 0.401 | 1.9408
|  | F - 5 (Grid A & 4) AFL -25.206 TOC -24.75 | 1 | 3.2 | 3.2 | 0.456 | 4.6694
|  | F - 11 (Grid B & 4) AFL -25.264 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.514 | 5.2634
|  | F - 17 (Grid C & 4) AFL -25.044 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.294 | 3.0106
|  | F - 24 (Grid D & 4) AFL -24.993 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.243 | 2.4883
08.06.2016 | 5.5 | F - 29 (Grid E & 1) AFL -25.544 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.794 | 8.1306
|  | F - 30 (Grid E & 2) AFL -25.381 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.631 | 6.4614
|  | F - 32 (Grid E & 4) AFL -24.991 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.241 | 2.4678
|  | F - 36 (Grid F-G & 1) AFL -25.316 to TOC -24.75 | 1 | 9.75 | 3.2 | 0.566 | 17.6592
|  | F - 39 (Grid F-G & 1) AFL -25.103 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.353 | 3.6147
|  | F - 43 (Grid G & 2) AFL -25.475 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.725 | 7.424
|  | F - 45 (Grid G & 4) AFL -25.254 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.504 | 5.161
|  | F - 48 (Grid H & 1-2) AFL -25.080 to TOC -24.75 | 1 | 11.025 | 3.2 | 0.33 | 11.6424
|  | F - 49 (Grid H & 3) AFL -25.082 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.332 | 3.3997
11.06.2016 | 5.5 | F - 31 (Grid E & 3) AFL -25.529 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.779 | 7.977
|  | F - 37 (Grid F & 2) AFL -26.102 to TOC -24.75 | 1 | 3.2 | 3.2 | 1.352 | 13.8445
|  | F - 38 (Grid F & 3) AFL -25.714 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.964 | 9.8714
|  | F - 44 (Grid G & 3) AFL -25.257 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.507 | 5.1917
|  | F - 50 (Grid H & 4) AFL -25.159 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.409 | 4.1882
|  | F - 53 (Grid J & 3) AFL -25.039 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.289 | 2.9594
|  | F - 54 (Grid J & 4) AFL -25.313 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.563 | 5.7651
13.06.2016 | 5.5 | F - 18 (Grid C & 5) AFL -25.096 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.346 | 3.543
|  | F - 25 (Grid D & 5) AFL -25.095 to TOC -24.75 | 1 | 3.2 | 3.2 | 0.345 | 3.5328
13.06.2016 | 7.1.1 | F - 16,17,23,24 EL(-24.75 to -23.25) | 4 | 12 |  | 1.5 | 72
13.06.2016 | 5.8.1 | F - 16,17,23,24 EL(-24.75 to -23.25) | 4 | 3 | 3 | 1.5 | 54

## Gen 1003
Name of Work | Construction of various buildings of Waste Management Plant and allied structures including Civil, Electrical and Mechanical works for FRFCF at Kalpakkam
TS No | C-0225/CV-1 (E)/FRFCF/IGCAR/2015 dt 12.01.2015
Contractor | M/s. Larsen & Toubro Limited, Chennai - 600 089
W.O NO | IGCAR/FRFCF/CV-1(E)/ETR-025/WO/2016/213 dt. 24.02.2016
Agt No. | IGCAR/FRFCF/CIVIL/A.41/2016 dt. 29.02.2016
RA-Bill No | RA BILL No. 03 (Zone-V) CC No.7732 | 1
Date of Measurement | Item No | Description of Work | No. | L | B | D | Content Area | Remarks
07.06.2016 | 7.1.1 | F - 509 (Grid G to K & 37a to 40) EL(-24.75 to -23.25) | 2 | 16.075 | - | 1.5 | 48.225
|  | F - 509 (Grid G to K & 37a to 40) EL(-24.75 to -23.25) | 2 | 16.3 | - | 1.5 | 48.9
07.06.2016 | 5.8.1 | F - 509 (Grid G to K & 37a to 40) EL(-24.75 to -23.25) | 1 | 16.3 | 16.075 | 1.5 | 393.0337

## Gen 1004
Name of Work | Construction of various buildings of Waste Management Plant and allied structures including Civil, Electrical and Mechanical works for FRFCF at Kalpakkam
TS No | C-0225/CV-1 (E)/FRFCF/IGCAR/2015 dt 12.01.2015
Contractor | M/s. Larsen & Toubro Limited, Chennai - 600 089
W.O NO | IGCAR/FRFCF/CV-1(E)/ETR-025/WO/2016/213 dt. 24.02.2016
Agt No. | IGCAR/FRFCF/CIVIL/A.41/2016 dt. 29.02.2016
RA-Bill No | RA BILL No. 03 (Zone-III) CC No.7605 | 1
Date of Measurement | Item No | Description of Work | Measurement Up todate |  |  |  |  | Remarks
|  |  | No. | L | B | D | Content Area

## Steel 1021
NAME OF WORK |  | Construction of various buildings of Waste Management Plant and allied structures including Civil, Electrical and Mechanical works for FRFCF at Kalpakkam
TS. No |  | C-0225/CV-1 (E)/FRFCF/IGCAR/2015 dt 12.01.2015
NAME OF CONTRACTOR |  | M/s. Larsen & toubro Limited, Chennai - 600 089
WORK ORDER NO |  | IGCAR/FRFCF/CV-1(E)/ETR-025/WO/2016/213 dt. 24.02.2016
AGT NO |  | IGCAR/FRFCF/CIVIL/A.41/2016 dt. 29.02.2016
RA BILL NO |  | RA BILL NO. 03 (Zone - V) CC NO. 7732
Date of Measur -ement | Item No | Description of Work | Dia of rod [mm] | Nos. | Length in Metres | 8 | 10 | 12 | 16 | 20 | 25 | 28 | 32 | 36 | Remarks
25.04.2016 | 8.1.1 | Footing ( F - 509 )
|  | Bottom N/S direction @150C/C | 20 | 107 | 18.73 | - | - | - | - | 2004.11 | - | - | - | -
|  | Bottom N/S direction laps | 20 | 107 | 0.94 | - | - | - | - | 100.58 | - | - | - | -
|  | Bottom E/W direction @150C/C | 20 | 109 | 18.425 | - | - | - | - | 2008.325 | - | - | - | -
|  | Bottom E/W direction laps | 20 | 109 | 0.94 | - | - | - | - | 102.46 | - | - | - | -
|  | Top E/W direction @150C/C | 20 | 109 | 18.425 | - | - | - | - | 2008.325 | - | - | - | -
|  | Top E/W direction laps | 20 | 109 | 0.94 | - | - | - | - | 102.46 | - | - | - | -
|  | Top N/S direction @150C/C | 20 | 107 | 18.73 | - | - | - | - | 2004.11 | - | - | - | -
|  | Top N/S direction laps | 20 | 107 | 0.94 | - | - | - | - | 100.58 | - | - | - | -
|  | Face Bars @ 250C/C | 20 | 6 | 63.99 | - | - | - | - | 383.94 | - | - | - | -
|  | Lap | 20 | 36 | 0.94 | - | - | - | - | 33.84 | - | - | - | -
| 8.1.2 | Column C5035,5036,5040,5041 (4nos)
|  | Verticals upto EL-23.25 | 36 | 48 | 1.687 | - | - | - | - | - | - | - | - | 80.976
| 8.1.1 | Column C5035,5036,5040,5041 (4nos)
|  | Master ring @ 150C/C | 10 | 44 | 3.22 | - | 141.68 | - | - | - | - | - | - | -
|  | Internal ring @ 150C/C | 10 | 40 | 2.464 | - | 98.56 | - | - | - | - | - | - | -
|  | Internal ring @ 150C/C | 10 | 40 | 2.132 | - | 85.28 | - | - | - | - | - | - | -
| 8.1.2 | Column C5037,5042 (2nos)
|  | Verticals upto EL-23.25 | 36 | 56 | 1.687 | - | - | - | - | - | - | - | - | 94.472
| 8.1.1 | Column C5037,5042 (2nos)
|  | Master ring @ 125C/C | 10 | 26 | 3.15 | - | 81.9 | - | - | - | - | - | - | -
|  | Internal ring @ 125C/C | 10 | 48 | 2.248 | - | 107.904 | - | - | - | - | - | - | -
|  | Internal links @ 125C/C | 10 | 12 | 1.1 | - | 13.2 | - | - | - | - | - | - | -
|  | Internal ring @ 125C/C | 10 | 48 | 1.762 | - | 84.576 | - | - | - | - | - | - | -
|  | Internal links @ 125C/C | 10 | 12 | 0.815 | - | 9.78 | - | - | - | - | - | - | -
| 8.1.2 | Column C5047
|  | Verticals upto EL-23.25 | 36 | 28 | 1.687 | - | - | - | - | - | - | - | - | 47.236
| 8.1.1 | Column C5047
|  | Master ring @ 100C/C | 10 | 15 | 3.65 | - | 54.75 | - | - | - | - | - | - | -
|  | Internal ring @ 100C/C | 10 | 42 | 2.284 | - | 95.928 | - | - | - | - | - | - | -
|  | Internal ring @ 100C/C | 10 | 42 | 2.214 | - | 92.988 | - | - | - | - | - | - | -
| 8.1.2 | Column C5046
|  | Verticals upto EL-23.25 | 36 | 20 | 1.687 | - | - | - | - | - | - | - | - | 33.74
| 8.1.1 | Column C5046
|  | Master ring @ 100C/C | 10 | 15 | 3.22 | - | 48.3 | - | - | - | - | - | - | -
|  | Internal ring @ 100C/C | 10 | 28 | 2.292 | - | 64.176 | - | - | - | - | - | - | -
|  | Internal ring @ 100C/C | 10 | 28 | 1.892 | - | 52.976 | - | - | - | - | - | - | -
| 8.1.2 | Column C5045
|  | Verticals upto EL-23.25 | 36 | 24 | 1.687 | - | - | - | - | - | - | - | - | 40.488
| 8.1.1 | Column C5045
|  | Master ring @ 100C/C | 10 | 15 | 3.15 | - | 47.25 | - | - | - | - | - | - | -
|  | Internal ring @ 125C/C | 10 | 14 | 2.248 | - | 31.472 | - | - | - | - | - | - | -
|  | Internal links @ 125C/C | 10 | 14 | 1.1 | - | 15.4 | - | - | - | - | - | - | -
|  | Internal ring @ 125C/C | 10 | 14 | 1.832 | - | 25.648 | - | - | - | - | - | - | -
|  | Internal links @ 125C/C | 10 | 12 | 0.85 | - | 10.2 | - | - | - | - | - | - | -
| 8.1.2 | SHW506
|  | Verticals upto EL-23.25 | 25 | 90 | 1.687 | - | - | - | - | - | 151.83 | - | - | -
| 8.1.1 | SHW506
|  | Spacer bars | 12 | 2 | 8.8 | - | - | 17.6 | - | - | - | - | - | -
| 8.1.2 | SHW510
|  | Verticals upto EL-23.25 | 28 | 62 | 1.687 | - | - | - | - | - | - | 104.594 | - | -
| 8.1.1 | SHW510
|  | Spacer bars | 12 | 2 | 6.1 | - | - | 12.2 | - | - | - | - | - | -
| 8.1.2 | SHW510
|  | Chairs | 25 | 257 | 4.18 | - | - | - | - | - | 1074.26 | - | - | -

## Steel 1022
NAME OF WORK |  | Construction of various buildings of Waste Management Plant and allied structures including Civil, Electrical and Mechanical works for FRFCF at Kalpakkam
TS. No |  | C-0225/CV-1 (E)/FRFCF/IGCAR/2015 dt 12.01.2015
NAME OF CONTRACTOR |  | M/s. Larsen & toubro Limited, Chennai - 600 089
WORK ORDER NO |  | IGCAR/FRFCF/CV-1(E)/ETR-025/WO/2016/213 dt. 24.02.2016
AGGREEMENT NO |  | IGCAR/FRFCF/CIVIL/A.41/2016 dt. 29.02.2016
RA BILL NO |  | RA BILL NO. 03 ( SWB ) CC NO. 7605
Date of Measur -ement | Item No | Description of Work | Dia of rod [mm] | Nos. | Length in Metres | 8 | 10 | 12 | 16 | 20 | 25 | 28 | 32 | 36 | Remarks
25.04.2016 | 8.1.1 | Footing ( F - 16,17,23,24 ) = 4nos
|  | Bottom N/S direction @150C/C | 20 | 80 | 5.47 | - | - | - | - | 437.6 | - | - | - | -
|  | Bottom E/W direction @150C/C | 20 | 80 | 5.39 | - | - | - | - | 431.2 | - | - | - | -
|  | Face Bars @ 250C/C | 20 | 24 | 11.24 | - | - | - | - | 269.76 | - | - | - | -
|  | Lap | 20 | 48 | 0.94 | - | - | - | - | 45.12 | - | - | - | -
|  | Top mat E/W direction @150C/C | 20 | 80 | 5.39 | - | - | - | - | 431.2 | - | - | - | -
|  | Top mat N/S direction @150C/C | 20 | 80 | 5.47 | - | - | - | - | 437.6 | - | - | - | -
| 8.1.2 | Column C120,121,130,131=4nos
|  | Verticals upto EL-23.25 | 36 | 64 | 1.687 | - | - | - | - | - | - | - | - | 107.968
| 8.1.1 | Column C120,121,130,131=4nos
|  | Master ring @ 100C/C | 10 | 60 | 3.22 | - | 193.2 | - | - | - | - | - | - | -
|  | Internal ring @ 100C/C | 10 | 112 | 2.482 | - | 277.984 | - | - | - | - | - | - | -
|  | Internal links @ 100C/C | 10 | 112 | 1.1 | - | 123.2 | - | - | - | - | - | - | -
| 8.1.2 | Column C120,121,130,131=4nos
|  | Chairs | 25 | 24 | 4.18 | - | - | - | - | - | 100.32 | - | - | -